## Sheet1
Project Plan
PROJECT DEADLINE: 6-JAN-20
Week | Start Date | End Date | Task description | Task type | Status | Resource
Week 1 | 2019-10-28 | 2019-11-01 | Understand how polynomials computations work | Mandatory | DONE | Internet tutorials
Week 1-3 | 2019-10-28 | 2019-11-15 | Learn more about Java programming | Mandatory | DONE | Internet tutorials and university courses
Week 3 | 2019-11-15 | 2019-11-17 | Find a way to implement the polynomials | Mandatory | DONE
Week 4 | 2019-11-18 | 2019-11-24 | Implement the monomial model | Mandatory | DONE
Week 5 | 2019-11-25 | 2019-11-29 | Implement the polynomial model | Mandatory | DONE
Week 5 | 2019-11-29 | 2019-12-01 | Understand how Java Regular Expressions(Regex) work | Mandatory | DONE | Internet tutorials
Week 6 | 2019-12-02 | 2019-12-06 | Implement a way to parse the input | Mandatory | DONE | Internet tutorials
Week 6,7 | 2019-12-07 | 2019-12-11 | Choose and implement a design pattern - MVC(model, view, controller) | Mandatory | DONE | Internet tutorials
Week 6,7 | 2019-12-02 | 2019-12-15 | Learn Java Swing for Graphical User Interface implementation | Mandatory | DONE | Internet tutorials
Week 8 | 2019-12-16 | 2019-12-22 | Create the Graphical User Interface | Mandatory | DONE
Week 9 | 2019-12-23 | 2019-12-25 | Separate unary operations buttons from binary operations buttons | Nice to have | TO DO
Week 9 | 2019-12-23 | 2019-12-27 | Link the Graphical User Interface with the Model in the Controller | Mandatory | DONE | Internet tutorials
Week 9 | 2019-12-27 | 2019-12-29 | Test for complete functionality | Mandatory | DONE
Week 10 | 2019-12-30 | 2020-01-05 | Improve the Graphical User Interface | Nice to have | TO DO
Week 10 | 2020-01-01 | 2020-01-05 | Solve the negative exponent issue | Nice to have | TO DO
Week 10 | 2020-01-03 | 2020-01-05 | Complete the special project feature | Nice to have | TO DO
Documentation Plan
Week | Start Date | End Date | Task description | Task type | Status | Resource
Week 10 | 2019-10-28 | 2020-01-05 | Design, write, use and update the project plan | Mandatory | DONE | University resources
Week 10 | 2019-12-30 | 2020-01-02 | Write technical documentation | Mandatory | DONE | Internet guides and university resources
Week 10 | 2020-01-03 | 2020-01-04 | Write user manual | Mandatory | DONE | Internet guides and university resources
Week 10 | 2020-01-04 | 2020-01-05 | Create .ppt presentation | Mandatory | DONE